## Overview
PHASE 1A ¦ Findings & Learning Dashboard
Pilot data integrity • SSB table 12134 • 2016 • Halden and Moss • 2 municipalities × 9 indicators
Pilot | Available numerical cells | Missing cells | Numeric recovery
Original codes 3101/3103 | 0 | 18 | 18
Historical codes 0101/0104 | 18 | 0 | 100%
How to interpret these findings
1. Original pilot: 18 null cells (status '.'); not zero financial performance.
2. Historic codes recovered 18/18 numbers; it does NOT verify accounting meaning.
3. Automated audit: 9/9 indicators have unit metadata; definition review pending.
4. Financial panel, municipality ranking and models have NOT been completed.
5. Next: audit nine definitions, annual scope, and disposisjonsfond.
Scientific approval: BLOCKED — exact definitions and 2016–2025 continuity
Read the Guide: docs/PHASE1A_FINDINGS_LEARNING_GUIDE.md

## Findings
Findings
Research evidence snapshot • 11 October 2026 • Local-terminal evidence, not an approved national dataset
Finding ID | Phase | Observed finding | Evidence and precise scope | Status | Evidence level | Evidence locator | Required next step
SETUP-001 | Project setup | VS Code project and GitHub repository exist | Repository main branch includes source catalogue, Python scripts, and four research records | PASS — repository verified | TECHNICAL | GitHub: marsman1976/norway-municipal-financial-performance | Use version control for next validated scripts
SETUP-002 | Initial raw inventory | Raw inventory initially found zero files | User terminal: Raw files found: 0; status UNAUDITED. Historical snapshot only; later pilot files exist | PASS — historical baseline | TECHNICAL | Initial inventory terminal output | Do not confuse initial zero files with current file inventory
API-001 | API connectivity | Six SSB/KLASS requests responded and passed basic structure checks | User terminal: Endpoint probe 6/6 passed, including KLASS changes | PASS — local run | TECHNICAL | endpoint_probe_manifest.csv (local, not independently inspected) | Save exact endpoint manifest with research records locally
BUG-001 | KLASS response format | KLASS changes endpoint used codeChanges rather than changes | SSB KLASS API integration tests; corrected probe passed 6/6 | RESOLVED — local run | TECHNICAL | https://github.com/statisticsnorway/klass | Preserve fix in scripts and problem log
PLAN-001 | Download planning | Table 12134 dry-run generated 30 requests with max 2700 planned cells | User terminal dry-run: 30 data requests; maximum 2700 cells | PASS — planning only | TECHNICAL | phase1a2_collection_manifest_20261011T152252Z.csv (local) | Do not mistake planning for downloaded data
PILOT-001 | Original 2016 pilot | Using 3101 and 3103 returned 18 missing values | User diagnostic: 2 regions × 9 indicators; 0 non-null; 18 null with status '.' | FAIL — data usability | DATA_QUALITY | Raw pilot SHA-256 6382ed57f44c31f658d91cb6b345c8a6e424eb7b9e428bddebec3fee9f817f24 (local report) | Keep original raw file immutable as evidence
DIAG-001 | Duplicate report handling | Diagnostic refused to overwrite an existing report | User traceback FileExistsError for pilot_12134_2016_diagnostic.txt after producing diagnosis | EXPECTED SAFEGUARD | TECHNICAL | phase1a_03_diagnose_pilot.py and user traceback | Read existing report; do not delete to conceal the previous failure
FIX-001 | Year-aware municipal codes | Validated historic 2016 codes 0101 Halden, 0104 Moss | Year-aware pilot checked source metadata and KLASS snapshot; user output reported numeric return | RESOLVED — pilot | DATA_QUALITY | scripts/phase1a_04_year_aware_pilot.py and local report | Extend year-aware selection to full collector, not just pilot
PILOT-002 | Corrected 2016 pilot | Corrected pilot produced all 18 finite numeric observations | User terminal: cells=18, non-null=18, null=0, missing-status counts={} | PASS — local run | DATA_QUALITY | SHA-256 181abcb10698d0b03886220c68564c0e55e9e3ba5e421a6b6e53cf1d3a9b5f02 | Review every numeric indicator's unit and accounting definition
AUDIT-001 | 2016 pilot automation | Nine of nine indicators had unit metadata; numeric/identity audit passed | User terminal automated gate PASS_NUMERIC_AND_IDENTITY__DEFINITION_REVIEW_PENDING | PASS — limited audit | DATA_QUALITY | pilot_12134_2016_20261011T162926430705Z_audit.json (local) | Read definition_review.csv and verify exact definitions
DEF-001 | Indicator definition signoff | All nine accounting definitions still require scientific signoff | Audit creates definition_review.csv with verification fields set to NO | OPEN — blocker | SCIENTIFIC | scripts/phase1a_05_audit_financial_pilot.py; generated definition_review.csv | Validate SSB footnotes, units, numerator, denominator and accounting scope
DEF-002 | Reserve fund construct | SSB free equity operational account is not automatically the same as disposisjonsfond | Design requires independently verified actual unrestricted reserve metric P2 | OPEN — blocker | SCIENTIFIC | KOSKG210000 and research methodology record | Do not substitute free equity operational account for primary reserve measure
CONT-001 | Longitudinal geography | 2016 pilot does not prove 2016–2025 code continuity | 2020 and 2024 structural changes require date-wise mapping and exclusion rules | OPEN — blocker | SCIENTIFIC | KLASS change history and study methodology | Audit annual 1:1 changes, mergers, splits, KOSTRA group changes
COV-001 | Historical accounting coverage | Detailed 2020-onward accounting sources cannot automatically fill 2016–2019 | Previous source inventory flagged period mismatch | OPEN — blocker | SCIENTIFIC | SOURCE_REGISTER.xlsx and study methodology | Find valid older equivalent or mark metric unavailable for full decade
COLL-001 | Full official data collection | Only a two-municipality one-year pilot has reported numeric success | No ten-year municipality panel, full metadata/footnotes, or all-source integrity report has been provided | NOT STARTED — full panel | SCIENTIFIC | Current local pilot outputs versus collection plan | Build corrected historical year-aware bulk collector after definition checks
CASE-001 | Strong/weak municipality selection | No municipalities have been classified or matched | No full eligible panel or validated primary indicators | BLOCKED | EMPIRICAL | Research protocol; no case-selection outputs | Wait for final source integrity and P1/P2/P3 definitions
HYP-001 | Financial causes of performance | No success/failure factor has been empirically established for the new paper | No cases selected and no models fitted | UNTESTED | EMPIRICAL | New study hypotheses only | Test later with cases and nationwide panel; avoid causal claims

## Indicators
Indicators
Research evidence snapshot • 11 October 2026 • Local-terminal evidence, not an approved national dataset
SSB indicator code | Working interpretation (verify official label) | Planned role | Metadata availability | Exact definition | 2016–2025 comparability | What must be verified
KOSAGD230000 | Net operating result as share of gross operating revenues | Primary outcome P1 | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | Operating result definition, year scope, classification
KOSAGD290000 | Annual accumulated surplus/deficit as share of gross operating revenues | Secondary financial balance | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | Whether annual accumulated metric maps to planned secondary outcome
KOSKG280000 | Working capital excluding pension premium deviation as share of revenues | Liquidity outcome P4 | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | Verify pension exclusion over time
KOSKG400000 | Net interest exposure as share of gross operating revenues | Debt/interest risk candidate | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | Interest-bearing exposure definition
KOSKG320000 | Net loan debt as share of gross operating revenues | Primary outcome P3 | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | Scope net versus gross and intermunicipal accounts
KOSAG110000 | Unrestricted revenues per capita | Baseline matching/control | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | Revenue sources, per-capita population denominator
KOSKG210000 | Free equity operational account | Secondary descriptive buffer ONLY | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | NOT the primary disposisjonsfond measure P2 without independent validation
KOSAGI10000 | Gross investment expenditures as share of gross operating revenues | Investment intensity candidate | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | Investment account and denominator
KOSAGI210000 | Self-investment financing as share of gross investment expenditures | Investment financing candidate | Metadata includes unit | REQUIRES SIGNOFF | REQUIRES SIGNOFF | Funding sources included in self-financing

## Problems
Problems
Research evidence snapshot • 11 October 2026 • Local-terminal evidence, not an approved national dataset
Issue ID | Problem encountered | Root cause or risk | Correction/action | Verification result | Status | Scientific implication
ERR-001 | SSB query returned 18 missing values for 2016 | Pilot used newer region codes (3101, 3103) for historical 2016 observations | Found in diagnostic and tested historic codes 0101, 0104 | After correction 18/18 numeric (2016, 2 municipalities) | RESOLVED IN PILOT | Must update FULL collector, not only pilot
ERR-002 | KLASS changes check failed despite HTTP 200 | Script expected JSON field 'changes' rather than official 'codeChanges' | Fixed parser and reran endpoint probe | 6/6 endpoint checks passed | RESOLVED | Maintain schema tests
ERR-003 | FileExistsError in diagnostic | Existing report protected by immutable-output rule | Read existing report; do not overwrite | Report preserved; not an SSB download error | EXPECTED SAFEGUARD | Use time-stamped outputs if rerunning
ERR-004 | Free equity operational account possibly mistaken for disposisjonsfond | Different accounting constructs risk invalid P2 reserve ranking | Keep as secondary indicator until actual disposisjonsfond is sourced and reconciled | Scientific approval still blocked | OPEN BLOCKER | Source correct reserve accounts before case selection
ERR-005 | Full collector is not year-aware | Older bulk script selects region codes from metadata without restricting validity per year | Adapt requests using annual KLASS codes, retain source provenance and annual coverage audits | Not yet implemented/verified for all years | OPEN BLOCKER | Do not run full extractor unchanged
ERR-006 | Detailed financial statements start after baseline for some sources | 2020+ detail lacks 2016–2019 equivalent in inventory | Locate historical bridge or mark ratio period-specific/not identifiable | Unresolved | OPEN BLOCKER | Do not silently interpolate or pretend ten-year comparability

## Roadmap
Roadmap
Research evidence snapshot • 11 October 2026 • Local-terminal evidence, not an approved national dataset
Step | Workstream | What was done or planned | Stage status | Required next action
0 | Study design | 2016–2025 with baseline 2016–2017, discovery 2018–2022, follow-up 2023–2025 | PREPARED | Freeze after feasibility/source audits
1 | VS Code and GitHub setup | Research skeleton, scripts and four living records | PASS | Keep commit history
2 | Official API connectivity | 6/6 SSB and KLASS metadata endpoint checks | PASS | Retain local probe manifest
3 | SSB bulk dry-run | 12134: 30 planned requests; max planned 2700 cells | PASS_PLANNING | Not proof of valid downloaded data
4 | Original pilot and diagnosis | 2016: 3101,3103; all 18 observations missing (.) | FAIL_DOCUMENTED | Preserve negative evidence
5 | Historical code correction | 2016: 0101,0104; 18/18 numeric observed | PASS_PILOT | Requires scientific definitions audit
6 | Independent numeric/identity audit | 9/9 unit metadata; automated gate PASS; scientific gate BLOCKED | PASS_LIMITED | Audit exact definitions and source notes
7 | Manual definition/footnote audit | Nine indicators + reserves, scope, years | BLOCKED | Next immediate task
8 | Year-aware full collection | All required 2016–2025 official finance, control and KLASS data | NOT_STARTED | Implement corrected code after definition audit
9 | Full data integrity and dataset ZIP | Reconciliation, completeness, source hashes, continuity and coverage | NOT_STARTED | Scientific signoff before case selection
10 | Matched case selection and finance analysis | Objective strong/weak matching; 10-year ratio analysis | NOT_STARTED | Wait for financial panel and verified reserve measure
11 | National statistical and predictive validation | Fixed effects, uncertainty, multiple tests, time validation | NOT_STARTED | No causal conclusions from two cases

## Glossary
Glossary
Research evidence snapshot • 11 October 2026 • Local-terminal evidence, not an approved national dataset
Term | Explanation | Example in our project | Evidence domain
Observation / cell | One value for one municipality, one indicator and one year | Two municipalities × nine indicators × one year = 18 cells | Technical
Null observation | No valid numeric value; do not replace automatically with zero | 18 null values in the original pilot | Data quality
Metadata | Field labels, codes, units, notes and other source documentation | Nine of nine indicator codes had unit metadata | Scientific
KLASS | Official annual municipality classification and history | 2016 0101 Halden and 0104 Moss are year-valid codes | Technical / scientific
JSON-stat2 status | Cell-level code explaining availability/other data conditions | Original pilot: '.' on 18 missing values | Data quality
SHA-256 | Hash of the exact bytes stored in a file | Pilot source hash provided by local script; not source-content proof | Reproducibility
Automated gate | Checks that a program can verify from files | 18 finite values, valid codes, matching dimensions | Technical
Scientific gate | Accounting and comparability judgments requiring source-backed signoff | Exact ratios, reserves and ten-year continuity remain pending | Scientific
Disposisjonsfond | Municipal unrestricted reserve fund, proposed P2 performance outcome | Must not be replaced automatically by free equity operational account | Scientific
Selection bias | Distortion when data or municipality choice depends on favorable results | Freeze rules; use baseline and later validation periods | Study design
Longitudinal continuity | Same actual entity or appropriately harmonized identity across years | Structural municipal reforms must be accounted for | Scientific
Empirical financial finding | Quantified result about real financial behavior with measured uncertainty | None has been produced in this new study yet | Empirical